## Dashboard
PROJECT DASHBOARD
Metric | Value
Total Tasks
Completed Tasks
In Progress Tasks
Blocked Tasks
Pending Sync
High Priority Tasks
Critical Priority Tasks
Overdue Tasks
Active Projects
Completion Rate

## Projects
project_id | project_name | jira_project_key | owner | start_date | end_date | status | description
PROJ001 | AI Task Manager | AIM | duong | 2026-03-01 | 2026-05-30 | Active | Build AI workflow automation system
PROJ002 | Mobile App Redesign | MAR | linh | 2026-02-15 | 2026-04-30 | Active | Complete UI/UX overhaul for mobile
PROJ003 | Database Migration | DBM | mai | 2026-03-10 | 2026-06-15 | Planned | Migrate from MySQL to PostgreSQL
PROJ004 | Customer Portal | CP | duong | 2026-01-01 | 2026-03-01 | Done | Self-service customer dashboard

## Tasks
task_id | project_id | task_name | description | assignee | reporter | priority | status | due_date | jira_issue_key | sync_status | last_updated
T001 | PROJ001 | Build REST API | Create authentication and authorization endpoints | duong | linh | High | In Progress | 2026-03-10 | AIM-23 | Synced | 2026-03-05 14:30
T002 | PROJ001 | Setup PostgreSQL | Configure database schema and indexes | mai | duong | Medium | In Progress | 2026-03-15 | AIM-24 | Synced | 2026-03-05 10:15
T003 | PROJ001 | Design UI Components | Create reusable React components library | linh | duong | Medium | To Do | 2026-03-20 | AIM-25 | Synced | 2026-03-04 16:45
T004 | PROJ001 | Setup CI/CD Pipeline | Configure GitHub Actions for deployment | duong | mai | High | To Do | 2026-03-12 | AIM-26 | Pending | 2026-03-05 09:00
T005 | PROJ002 | User Research | Conduct interviews and surveys | linh | linh | Critical | Done | 2026-02-20 | MAR-12 | Synced | 2026-02-25 11:20
T006 | PROJ002 | Wireframe Design | Create low-fidelity wireframes | linh | linh | High | Done | 2026-02-28 | MAR-13 | Synced | 2026-03-01 15:30
T007 | PROJ002 | High-fidelity Mockups | Design pixel-perfect screens | linh | duong | High | In Progress | 2026-03-15 | MAR-14 | Synced | 2026-03-05 13:00
T008 | PROJ002 | Implement Navigation | Build bottom tab and drawer navigation | mai | linh | Medium | To Do | 2026-03-25 | MAR-15 | Synced | 2026-03-03 10:00
T009 | PROJ003 | Assess Current Schema | Document existing database structure | mai | mai | Medium | To Do | 2026-03-20 |  | Pending | 2026-03-05 08:30
T010 | PROJ003 | Migration Plan | Create detailed migration strategy | mai | duong | High | To Do | 2026-03-25 |  | Pending | 2026-03-05 08:30
T011 | PROJ004 | Backend API | Build customer data endpoints | duong | linh | High | Done | 2026-02-15 | CP-45 | Synced | 2026-02-20 16:00
T012 | PROJ004 | Frontend Dashboard | Create customer analytics dashboard | linh | duong | Medium | Done | 2026-02-25 | CP-46 | Synced | 2026-02-28 14:00
T013 | PROJ001 | Write Unit Tests | Achieve 80% code coverage | duong | mai | Low | Blocked | 2026-03-18 | AIM-27 | Synced | 2026-03-05 11:00
T014 | PROJ002 | Dark Mode Support | Implement theme switching | mai | linh | Low | To Do | 2026-04-05 | MAR-16 | Pending | 2026-03-04 09:30
T015 | PROJ001 | Setup Monitoring | Configure Sentry and DataDog | mai | duong | Medium | To Do | 2026-03-22 |  | Pending | 2026-03-05 15:00

## Task Updates
update_id | task_id | update_type | old_value | new_value | updated_by | update_time
U001 | T002 | status_change | To Do | In Progress | mai | 2026-03-05 10:15
U002 | T001 | comment |  | Implemented OAuth2 flow | duong | 2026-03-05 14:30
U003 | T005 | status_change | In Progress | Done | linh | 2026-02-25 11:20
U004 | T006 | status_change | In Progress | Done | linh | 2026-03-01 15:30
U005 | T007 | status_change | To Do | In Progress | linh | 2026-03-05 13:00
U006 | T001 | priority_change | Medium | High | linh | 2026-03-04 09:00
U007 | T011 | status_change | In Progress | Done | duong | 2026-02-20 16:00
U008 | T012 | status_change | In Progress | Done | linh | 2026-02-28 14:00
U009 | T013 | status_change | To Do | Blocked | duong | 2026-03-05 11:00
U010 | T013 | comment |  | Blocked by API changes | duong | 2026-03-05 11:00

## Team Members
user_id | name | email | jira_account_id | role
U01 | duong | duong@company.com | 5f8a9b2c3d4e5f6a | Tech Lead
U02 | mai | mai@company.com | 6g9b0c3d4e5f6a7b | Backend Developer
U03 | linh | linh@company.com | 7h0c1d4e5f6a7b8c | Frontend Developer

## Sync Log
log_id | task_id | action | jira_issue | status | message | timestamp
L001 | T001 | create | AIM-23 | success | Issue created successfully | 2026-03-03 09:15
L002 | T002 | create | AIM-24 | success | Issue created successfully | 2026-03-03 09:15
L003 | T003 | create | AIM-25 | success | Issue created successfully | 2026-03-03 09:16
L004 | T001 | update | AIM-23 | success | Status updated | 2026-03-05 14:30
L005 | T002 | update | AIM-24 | success | Status updated | 2026-03-05 10:15
L006 | T004 | create | AIM-26 | failed | Authentication error | 2026-03-05 09:00
L007 | T007 | update | MAR-14 | success | Status updated | 2026-03-05 13:00
L008 | T013 | update | AIM-27 | success | Status updated to Blocked | 2026-03-05 11:00